## Project Plan
[15 empty] | Client |  |  |  | Bank Holiday/ Weekend
|  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12
HEALIX 006 |  | 2017-01-09 | [6 empty] | 2017-01-16 | [6 empty] | 2017-01-23 | [6 empty] | 2017-01-30 | [6 empty] | 2017-02-06 | [6 empty] | 2017-02-13 | [6 empty] | 2017-02-20 | [6 empty] | 2017-02-27 | [6 empty] | 2017-03-06 | [6 empty] | 2017-03-13 | [6 empty] | 2017-03-20 | [6 empty] | 2017-03-27
|  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
 | time axis 2024-02-19 to 2024-05-12
Project Initiation Stage | Responsible
Hold the risk meeting to identify & asses risk | Project Manager | bar: 2024-02-19 to 2024-02-23
Compile project stakeholder register | Project Manager | bar: 2024-02-19 to 2024-02-23
Create the communication plan for the project | Project Manager | bar: 2024-02-19 to 2024-02-23
Compile raid log and lessons learnt document | Project Manager | bar: 2024-02-19 to 2024-02-23
Create your teams Trello board and invite all team members | Project Manager | bar: 2024-02-19 to 2024-02-23
Conduct Gap Analysis | Business Analyst | bar: 2024-02-19 to 2024-02-23
Create a project scope document | Business Analyst | bar: 2024-02-19 to 2024-02-23
Create Project Proposal | Project Manager | bar: 2024-02-26 to 2024-03-01
Draft a Project Brief | Project Manager | bar: 2024-02-26 to 2024-03-01
Create your project brief based on the project cost. | Project Manager | bar: 2024-02-26 to 2024-03-01
Ensure everyone is working on their deliverables | Project Manager | bar: 2024-02-26 to 2024-03-01
Submit Project status report. | PMO | bar: 2024-02-26 to 2024-03-01
Prepare requirements gathering workshop agenda | Business Analyst | bar: 2024-02-26 to 2024-03-01
Hold requirement workshop with the team (using personas) | Business Analyst | bar: 2024-02-26 to 2024-03-01
Identify and document high level and low level requirements | Business Analyst | bar: 2024-02-26 to 2024-03-01
Start writing user stories and acceptance critieria. | Business Analyst | bar: 2024-02-26 to 2024-03-01
Ensure to prioritize requirements (MoSCoW). | Business Analyst | bar: 2024-02-26 to 2024-03-01
Obtain approval | Program Manager | bar: 2024-02-26 to 2024-03-01
Project Planning | Responsible
Compile a competitive Analysis Document | Project Manager | bar: 2024-03-04 to 2024-03-08
Create work brakedown structure (WBS). | Project Manager | bar: 2024-03-04 to 2024-03-08
Update Trello board | Project Manager | bar: 2024-03-04 to 2024-03-08
Hold the weekly meeting with program manager | Project Manager | bar: 2024-03-04 to 2024-03-08
Submit project status report (PSR) and RAID Log. | PMO | bar: 2024-03-04 to 2024-03-08
Draft user stories and acceptance criteria document | Business Analyst | bar: 2024-03-04 to 2024-03-08
Get Familiar with the trello board and move cards to show progress on deliverables | Business Analyst | bar: 2024-03-04 to 2024-03-08
Create project high level plan on MS project | Project Manager | bar: 2024-03-11 to 2024-03-15
Update Trello board | Project Manager | bar: 2024-03-11 to 2024-03-15
Submit your Project status report (PSR | Project Manager | bar: 2024-03-11 to 2024-03-15
Create business case document | Project Manager | bar: 2024-03-11 to 2024-03-15
Update Trello board with signed-off documents. | Business Analyst | bar: 2024-03-11 to 2024-03-15
Submit updated BA work plan | Business Analyst | bar: 2024-03-11 to 2024-03-15
Conduct SWOT Analysis | Business Analyst | bar: 2024-03-11 to 2024-03-15
Obtain approval | Program manager
Design Stage | Responsible
Create an Azure board and ensure everyone is added | Project Manager | bar: 2024-03-18 to 2024-03-22
Update Trello board | Project Manager | bar: 2024-03-18 to 2024-03-22
Submit PSR | Project Manager | bar: 2024-03-18 to 2024-03-22
Send in Assessment for Week 5 | Project Manager | bar: 2024-03-18 to 2024-03-22
Product Requirement Document | Project Manager | bar: 2024-03-18 to 2024-03-22
Create your Process Maps. | Business Analyst | bar: 2024-03-18 to 2024-03-22
Submit updated Work Plan. | Business Analyst | bar: 2024-03-18 to 2024-03-22
Submit PSR (Week 1 to Week 6) and updated RAID Log | Project Manager
Send end of design stage report | Project Manager
Send development stage plan document. | Project Manager
Revise the AGILE Scrum Guide | Project Manager
Send in Assessment for Week 6 | Project Manager
Create Wireframes | Business Analyst
Submit updated work plan | Business Analyst
Revise the AGILE Scrum Guide | Business Analyst
Development Grooming & Planning | Responsible
Ensure a developer and tester are added to the team by sending an email to admin@almondcareers.com requesting for that. | Project Manager
Ensure all work items are addedd to Azure. | Project Manager
Ensure all decuments from previous week deliverables are signed off. | Project Manager
Submit PSR and Send in assessment for week 7. | PMO
Update the trello board | Project Manager
Create a Business Model Canvas | Business Analyst
Ensure Developer and Tester are well aligned | Business Analyst
Work with Tester oncreating Test plan based on acceptance criteria | Business Analyst
Ensure Tester hands in User Acceptance Test document (UAT) | Business Analyst
Join the project team | Developer
Send an intro e-mail on basecamp | Developer
Review Requirements Document, Process Maps and Wireframes. | Developer
Hold a welcome meeting with the team and study the Software Terms and Techniques document with them. | Developer
Join the project team | Tester
Send an intro e-mail on basecamp. | Tester
Understand scope document. | Tester
Work with the team on Test Plan and test case documentations. | Tester
Hold a welcome meeting with the team | Tester
Sprint Development | Responsible | bar: 2024-03-18 to 2024-03-22
Ensure everyone is added on the Azure board | Project Manager | bar: 2024-03-18 to 2024-03-22
Ensure all requirements are added on the board | Project Manager | bar: 2024-03-18 to 2024-03-22
Join the Sprint Planning meeting | Project Manager | bar: 2024-03-18 to 2024-03-22
Update the Trello Board | Project Manager | bar: 2024-03-18 to 2024-03-22
Submit PSR | PMO
Ensures there are updates from the developer | Project Manager
Send in Assessment for Week 8 | Project Manager
Work with Developer to validate requirements | Business Analyst
Align all documents with the developer | Business Analyst
Join the Sprint planning meeting | Business Analyst
Support the development team | Business Analyst
Update the Trello board | Business Analyst
Send in Assessment for Week 8 | Business Analyst
Understand the Scope document | Developer
Conclude design with BA(s) | Developer
Validate Process Maps | Developer
Validate User stories and acceptance critieria | Developer
Add everyone on the Azure board | Developer
Conduct Sprint planning meeting for sprint 1. | Developer
Validate test cases | Business Analyst
Validate UAT document | Business Analyst
Groom Team members on how to conduct UAT | Business Analyst
Prepare test documents for Sprint 1. | Business Analyst
Update Trello Board | Project Manager
Submit PSR and RAID Log, ensure the Lessons Learnt Log is well updated. | Project Manager
Ensure UAT is conducted with the tester after the sprint 1 demo. | Business Analyst
Send in updated BA Work Plan and Assessment for Week 9. | Business Analyst
Prepare a team excercise on BA related topics (45 mis with the entire team) | Business Analyst
Continue with tasks for Sprint 1 and send in daily updates. | Developer
Conduct Demo for Sprint 1 with the team | Developer
Test Sprint 1 functionalties | Business Analyst
Join the Sprint 2 Planning meeting | Project Manager
Update the Trello board | Project Manager
Submit PSR | PMO
Ensures there are updates from the developer | Project Manager
Prepare a team excercise on Scrum (45 mins questions and answers on related topics) | Project Manager
Support the development team | Business Analyst
Update the Trello board | Business Analyst
Send in Assessment for Week 10 | Business Analyst
Conduct Sprint 2 planning meeting | Developer
Continue with tasks for Sprint 2 and send in daily updates | Developer
Prepare test documents for Sprint 2 | Tester
Update Trello Board | Project Manager
Submit PSR | PMO
Prepare End of the Project Report | Project Manager
Ensure UAT is conducted after the demo for sprint 2 | Business Analyst
Send in Assessment for Week 11 | Business Analyst
Continue with tasks for Sprint and send in daily updates. | Developer
Conduct Demo for Sprint 2 with the team. | Developer
Test Sprint 2 functionalties | Tester
Closure | Responsible
Hand in your End of Project Report. | Project Manager
Ensure an End of Project Meeting is conducted with the program manager. | Project Manager
Conduct final UAT | Business Analyst
Coordinate final UAT session | Tester
Formulas:
WEEK 2 = SUM([WEEK 1]+7)
WEEK 3 = SUM([WEEK 2]+7)
WEEK 4 = SUM([WEEK 3]+7)
WEEK 5 = SUM([WEEK 4]+7)
WEEK 6 = SUM([WEEK 5]+7)
WEEK 7 = SUM([WEEK 6]+7)
WEEK 8 = SUM([WEEK 7]+7)
WEEK 9 = SUM([WEEK 8]+7)
WEEK 10 = SUM([WEEK 9]+7)
WEEK 11 = SUM([WEEK 10]+7)
WEEK 12 = SUM([WEEK 11]+7)