## Guide
Project Initiation
Stakeholder's Register
RAID Log
Risk: a future event that may have an impact on any one of five elements within the project (finances, strategy, reputation, operations, compliance).
Assumptions: things you assume are in place which contribute to the success of the project.
Issues: a problem affecting the project currently.
Dependencies : exists when an output from one piece of work or project is needed as mandatory input for another project or piece of work
GAP Analysis
Current State: Manual, paper-based ticketing system
Actions: Developing an application to ease the process of ticket production, ticket access and ticket sale
Desired State: To have a website
Project Scope
Justification: Paper tickets are are becoming obsolete and the ticketing space has gone digital
Scope Description: Features to be built - Account, Tickets, Contact Us, Events, Social, Support/Live Chat, History
Business Objective
Project Brief
About the Project: Background, Current State, Desired State, Summary of output
Resources
Procurement: Terms of Contract
Development Approach
Project Scope
RAID Log
Estimated Cost
Stakeholder Map
Project Control
Team's Roles and Responsibilities
Team Structure
Project Timeline and Key Milestones
Project Proposal
Requirements Document
High-Level Requirements
Low-Level Requirements
Project Planning phase
Competitive Analysis
Work Breakdown Structure (WBS)
Business Case
SWOT Analysis
Project Design phase
Product Requirement Document
Process Maps
Wireframes
Project Development phase
Business Model Canvas
Test Plan
User Acceptance Test (UAT) Doc.
Project Closure
End of Project Report
Final UAT Session

## Proj phase Lev
WORK BREAKDOWN STRUCTURE
Website Application
Initiation Stage | Planning Stage | Design Stage | Development Stage | Closure
Stakeholder Register | Competitive Analysis | Product Requirement Doc | Business Model Canvas | End of Project Report
Date - 16/04/24 | Date - 16/04/24 | Date - 24/04/24 | Date - 26/04/24 | Date - 18/04/24
Owner - PM | Owner - PM | Owner - PM | Owner - BA | Owner - PM
RAID Log | WBS | Process Maps | Test Plan | Final UAT session
Date - 16/04/24 | Date - 16/04/24 | Date - 24/04/24 | Date - 26/04/24 | Date - 18/04/24
Owner - PM | Owner - PM | Owner - BA | Owner - BA | Owner - BA
GAP Analysis | Business Case | Wireframes | UAT Doc.
Date - 16/04/24 | Date - 16/04/24 | Date - 24/04/24 | Date - 26/04/24
Owner - BA | Owner - PM | Owner - BA | Owner - Testers
Project Scope | SWOT Analysis | End of Design Stage Report | Sprint 1
Date - 16/04/24 | Date - 16/04/24 | Date - 24/04/24 | Date - 26/04/24
Owner - BA | Owner - BA | Owner - PM | Owner - SCRUM Team
Requirements Document | High Level Plan - MS Project | Development Stage Plan | Sprint 2
Date - 16/04/24 | Date - 16/04/24 | Date - 24/04/24 | Date - 26/04/24
Owner - BA | Owner - PM | Owner - PM | Owner - SCRUM Team
Project Brief | BA Work Plan
Date - 16/04/24 | Date - 16/04/24
Owner - PM | Owner - BA
Project Proposal
Date - 16/04/24
Owner - PM

## Deliverables Level
WORK BREAKDOWN STRUCTURE
Website Development
ACCOUNT | ABOUT US | NOTIFICATIONS | CONTACT US | FAQ | PAYMENTS
Sign Up | Display About us | Notification Display | Contact Display | Display FAQ | Payment options
Date - 16/04/24 | Date - 16/04/24 | Date - 16/04/24 | Date - 16/04/24 | Date - 20/04/24 | Date - 20/04/24
Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers
Log in | Edit About us | Notification Issues | Contact Us Form | Edit FAQ | Payments Issues
Date - 16/04/24 | Date - 16/04/24 | Date - 16/04/24 | Date - 16/04/24 | Date - 24/12/22 | Date - 20/04/24
Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers | Owner - Developers/Testers
Sign Up Issues | Delete About us |  | Contact Issues | Delete FAQ
Date - 16/04/24 | Date - 16/04/24 |  | Date - 16/04/24 | Date - 20/04/24
Owner - Developers/Testers | Owner - Developers/Testers |  | Owner - Developers/Testers | Owner - Developers/Testers
Login Issues | About us Issues |  |  | FAQ Issuess
Date - 16/04/24 | Date - 16/04/24 |  |  | Date - 20/04/24
Owner - Developers/Testers | Owner - Developers/Testers |  |  | Owner - Developers/Testers