## StakeHolder Register
Stakeholder Register
| Project Name | Healix 006
| Project Phase | Initiation Phase
| Document Type | Stakeholder Register
| Draft | First Draft
| Date | 22.04.2024
S/N | Name of Stakeholder | Designation | Department | Role in Project | Type of Stakeholder | Type of Communication | Expectations | Influence on project outcome
1 | Henry Mbadiwe | Director PM | C-Suite | Project Initiator | Internal | Weekly Video Conference | On- time, On-budget delivery | Influencer
2 | Haske Ovye | Program Manager | Technology Applications | Project Support | Internal | Weekly Video Conference, WhatsApp, Basecamp, Email | Measurable business success, On-time delivery. | Supporter
3 | Nkechi Bardey | Team Lead/Product Owner | Director Tech | Project Delivery | Internal | Weekly update via email | Clear requirements, On-time signoffs, skilled resources | Influencer
4 |  | Project Managers | PMO | Project Delivery | Internal | Daily Video Conference, WhatsApp, Basecamp, E-mail, Telephone | On- time, On-budget and within scope delivery, Clear requirements, Continuous Integration and Continuous delivery CI/CD | Influencer
5 |  | Business Analysts | PMO | Project Delivery | Internal | Daily Video Conference, WhatsApp, Basecamp, E-mail, Telephone | Clear requirements, On-time and within scope delivery, Continuous Integration and Continuous delivery CI/CD | Influencer
6 |  | Developers | Technology Development | Product Development | Internal | Daily Video Conference, WhatsApp, Basecamp, E-mail, Telephone, JIRA | Continuous Integration and Continuous delivery CI/CD | Influencer
7 |  | Testers | Technology Development | Quality Assurance | Internal | Daily Video Conference, WhatsApp, Basecamp, E-mail, Telephone, JIRA | Continuous Integration and Continuous delivery CI/CD | Influencer
8 |  | Project Manager (Ticketing company) | Technology Applications | Project Delivery | External | Weekly update via email | On- time, On-budget delivery, Clear requirements, Continuous Integration and Continuous delivery CI/CD | Influencer
9 |  | Head of Admin | Head of Administration | Payment Implementation | External | Weekly update via email | On- time, Continuous Integration and Continuous delivery CI/CD | Supporter
10 |  | User Experience (UX) Designers | Technology Development | User engagement | Internal | Video Conference, WhatsApp, E-mail | Continuous Integration and Continuous delivery CI/CD | Supporter
11 |  | Content Writers | Technology Development | Content Development | Internal | Video Conference, WhatsApp, E-mail | Continuous Integration and Continuous delivery CI/CD | Supporter
12 |  | Legal Officer | Legal | Compliance with Regulations & Reviewing Policy documents | Internal | Update via Email, Video Conferencing, Physical meetings with regulators (if required) | On-time approvals, Continuous delivery | Supporter
13 |  | End User (Admin ) | Customer Relations | Provide feedback | External | Coming soon page on website and Email messages to subscribers | User friendly interfaces, Quality delivery | Supporter
14 |  | Web Hosting Company | Technology Development | Website accessibility / availability | External | Support via email, live chat, telephone | On- time, Continuous Integration and Continuous delivery CI/CD | Supporter
15 |  | UK Information Commissioners Office (ICO) | Regulator | Project Compliance | External | Policy documents | Data Governance and Data Protection | Supporter
16 |  | Anti-Money Laundering Agency | Regulator | Project Compliance | External | Approval requests, Emails, In-person meetings | Regulatory compliance | Supporter